**UW-W Strategic Planning Committee Timeline (Fall 2016)**

|  |  |
| --- | --- |
| September 2016 | *Final Development Phase*   * Strategic Planning Committee (SPC) meets to discuss current draft of Goals and Objectives * SPC recommends draft of Goals and Objectives to Chancellor for broader campus/community/governance feedback * SPC establishes a plan for development of KPIs and actions * SPC establishes a plan for obtaining campus/community/governance feedback (e.g., listening sessions) * Website updated w/ current draft of Goals and Objectives, feedback opportunities on Goals and Objectives |
| October/November 2016 | *Constituency Feedback*   * SPC implements plan for obtaining campus/community/governance feedback on Goals and Objectives * Website updated w/ feedback opportunities on Goals and Objectives * SPC meets to review campus/community/governance feedback regarding Goals and Objectives and make final recommendations * SPC meets to discuss KPIs and top-level actions * SPC recommends draft of KPIs and top-level actions to Chancellor for broader campus/community/governance feedback * Website updated w/ Goals and Objectives feedback opportunities on KPIs and top-level actions |
| November/December  2016 | *Recommendation Phase*   * SPC meets to review campus/community/governance feedback regarding KPIs and top-level actions and make final recommendations * SPC meets with Chancellor to discuss recommended Strategic Plan |
| January 2017 | *UW-W Strategic Plan Reveal*   * UW-W Strategic Plan shared with the UW-W campus and community |